## 33 Quiz Qs
Q number | Topics | Question | Right answer | Wrong answer 1 | Wrong answer 2 | Wrong answer 3 | Wrong answer 4 | Answer notes
CLO-1 Translate organisational strategy to project deliverables
1 | project initiation phase | Which of the following activites forms part of project initiation? | Identify stakeholders | Solicit requirements | Develop the project management plan | Formulate scope | Monitor risks | PMBOK part 2, slides 2-6
2 | the project charter | Which of the following is not a purpose of the project charter document? | Presenting the business case | Authorizing the project | Recording the existence of the project | Committing resources to the project | Identifying the project manager | PMBOK part 1 Sec. 4.1 slides 7-9
3 | projects in organisations | Which is not an advantage of adopting a strong matrix project organisation over a functional organisation structure? | Excellent nuturing of engineering knowledge in the organisation | Direct oversight by PM to limit spending on non-project activities | Efficient coordination of activites beween different functional departments | Project team has a high degee of authority to expedite and execute project work | Ability to easily convene cross-functional teams | Bernie Wk 2 case study 7 Q11 wk 6 quiz |  | not in answers
4 | projects in organisations | Which of the following has the utmost importance in defining project success? | Strategic benefit | Completion within allowed time | Budgetary compliance | Product quality and performance | Scope delivery | Bernie wk 2 last slide
5 | projects in organisations | A disadvantage of using NPV as a method of project financial evaluation is: | It favours larger projects over smaller projects, regardless of rates of return | It favours smaller projects over larger projects, regardless of rates of return | It ignores the time value of money | It requires more effort to calculate than ERR | Compares rates of return regardless of project size | Bernie Q5; Bernie wk2 sl28
6 | PMBOK | In PMI’s talent triangle of talents required of a Project Manager, the content of this course is mostly: | The technical knowledge and skills in the domain of project management | The requisite skills and behaviour to guide, motivate and direct a team | Expertise in a relevant industry to deliver business outcomes | Strategic and Business Management | Something else (none of these options) | Bernie wk2 sl52 and PMBOK 3.4.1
CLO-2 Formulate Project Scope
7 | Requirements | What approach can be used to validate the defined relationships (between customer requirements and technical parameters) in QFD approach? | Using test data | Voice of engineers | Voice of customers | Defining correlation between technical parameters |  | Shiva Q11
8 | Requirements | At which step of QFD we define special emphasis for customer requirements? | Competitive analysis | Customer requirement (voice of customers) | Technical comparison | Interactions |  | Shiva Q8
9 | design tools | What choice does not describe the QFD approach? | A product out approach | A market in approach | Allowing integrated thinking in a cross-functional team | translates customer requirement to technical requirements |  | Shiva Q5
10 | design tools | What does system validation mean? | Checking the compliance of any element with its purpose | Checking the compliance of any element with its system architecture | Embodying system’s function with system structure | Embodying system function with system behaviour | Embodying system function as combination of structure and behaviour | Shiva Q4
11 | WBS | Creating the WBS: | Provides a complete framework for what must be delivered | Is performed once, at the start of the project planning | Is performed continuously throughout project iterations | Is independent of engineering design | Is part of project initiation | PMBOK 5.4; | use PMBOK
12 | WBS | The WBS completely and only defines: | Project scope | Project activities | Project deliverables | Work packages | Relatationships between deliverables | PMBOK 5.4.3.1; wk2 sl 49 | use PMBOK
CLO-3 Select Project Management Methods
13 | Requirements | An example of a non-functional, mandatory product requirement for an industrial control system could be: | The control system shall perform with an interlock error probability of 1 in 10,000 per annum | The control system should enable operators to select the desired actuator | The control system shall display a warning light if the radiation dose rate is too high | The vendor shall provide documentation supporting the failure rate calculations for the control system | The control system shall maintain a log of all user interractions for the preceding 10 years. | PMBOK 5.2.3.1, week 2 slide 8
14 | Stakeholders | The project sponsor is not | part of the project team | a stakeholder | a member of the steering committee | a person | internal to the project executing organisation | Week 1 slide 53
15 | Cost | In estimating cost and time, reliable historical data and well-understood project parameters are essential to support: | Parameteric estimates | Bottom-up estimates | Top-down approaches to estimating | Bottom-up approaches to estimating | Consensus methods | Week 4 sl 9-13; PMBOK 6.4.2.3
16 | Cost | Three-point estimating tools can be used to provide an indication of: | cost, time and risk | cost and time | cost | time and risk | time | Week 4 sl 21; PMBOK 7.2.2.5
17 | Schedule | The forward pass calculation through a project network diagram calculates: | The earliest start and earliest finish date of each activity | The critical path | The late start and late finish date for each activity | The total slack | The earliest start and latest finish date of each activity | Week 4 sl 51
18 | Schedule | Two disadvantages of fast tracking a schedule are, respectively: | Increased schedule sensitivity, increased technical risk | Longer critical path, increased schedule risk | longer critical path, higher costs | Schedule compression, increase in technical risk | Reduction in sensitivity, longer critical path | Week 4 sl 53-54
19 | Schedule | Crashing as a strategy for schedule compression: | Does not automatically increase risk, but will ususally cost the project more to complete the same amount of work | Should be avoided because it increases technical risks to project delivery | Relies on modifying the interdependencies between activities | Does not really help to increase project progress | Is a cost effective way to accelerate progress, but increases technical risks to project delivery | Week 4 sl 53-54
20 | Risk | Developing and agreeing contingecy plans with the stakeholders is a strategy for | Risk acceptance | Risk mitigation | Risk avoidance | Risk transfer | Risk prioritisation | Week 4 sl 72; PMBOK 11.5.2.4 | use PMBOK as well
21 | Risk | If four risk response strategies are: Transfer, Avoid, Mitigate, and Escalate, then the inherently similar corresponding strategies for responding to opportunites are, respectively: | Share, Exploit, Enhance, and Escalate | Share, Exploit, Enhance, and Accept | Exploit, Share, Escalate, and Transfer | Exploit, Avoid, Enhance, and Escalate | Exploit, Escalate, Enhance, and Avoid | Week 4 sl 72/84 and PMBOK 11.5.2.4 and 11.5.2.5
22 | Risk | What is the weakness of a risk-based approach to managing safety? | May allow severe hazards to go un-mitigated if the likelihood of their risk event is assessed as sufficently rare | Wasting resources on planning for improbably unlikely events | Requires a lot of theoretical effort, when risks are best handled by practical measures | Does not take into account the biggest hazards | Results in expensive treatment of very unlikely and unimportant events | Week 4 sl 97-91
23 | Agile | What is not one of the principles of Lean and/or Kanban? | Increase work in progress | Visualising the workflow | Reduce transportation | Eliminate waiting | Manage the flow | Dirk Sl 38 and wk5/6 quiz Q 30 | repeat
24 | Agile | If you had to choose one option, which is probably best for success in your project(s) ? | A highly functioning team with basic tools | Advanced tools used by a mediocre team | Carefully perfected system of work | Advanced tools and elaborate process | Use Agile methodologies | Dirk Sl 42 and wk5/6 quiz Q 29 | repeat
25 | Resources | Conflict management and influencing, and well as planning recognition and rewards, are all part of: | Developing a team | Acquiring resources | Managing communciations | Managing quality | Decisionmaking | PMBOK 9.4.2.4
CLO-4 Integrate & Justify Project Plans
26 | Risk and contingency | Which of the following does not well describe the contingnecy reserve budget? | Normally requires change control process and approval of project sponsor to be expended | Is for funding 'known unknowns' uncovered as a result of the risk management process | Amount of reserve funding depends on the risks identifed, and treatment for these risks | Part of the cost baseline | May be used for rework | PMBOK 7.2.2.6 and 7.3.3.1, week 4 slide 75,77
27 | Risk and contingency | An approved scope change request will often imply: | Spending more of the management reserve budget | Spending more of the contingency reserve budget | No change to the scope baseline | Updating the project charter | Revising the project benefits | week 4 slide 75
28 | PMBOK input/output Q | Once all stakeholders have been analysed in terms of their requirements and expectations, a next step would be to: | Formulate a plan to engage with each stakeholder | Identify the stakeholders | Calculate how much profit can be derived from each stakeholder | Plan how to prioritise the needs of the largest number of stakeholders | Convene a meeting of all stakeholders and ask them for their views on the project | Quiz wk 2 Q3, PMBOK 13 | repeat
CLO-5 Evaluate Progress and Interpret Success in Projects
29 | EVM | Looking at a project that EV analysis shows has an SPI = 1.04 would allow you to conclude: | The project is ahead of schedule, but would require Gantt chart analysis to forecast its end schedule status | The project is under budget and is forecast to finish under budget | The project is under budget and ahead of schedule | The project is ahead of schedule and is forecast to finish ahead of schedule |  | Bernie Q14
30 | EVM | Earned Value (EV) Analysis is a: | Cost management technique | Revenue management technique | Profit management technique | A scope management technique | A scope management tool | Bernie Q12
31 | Project controls | In customer funded project changes, a potential downside for the customer is: | The supplier will have the negotiating power with respect to price/schedule/scope | The change may be disruptive to the management of the project | The change can raise disputes | The change can cause reputational damage to the customer |  | Bernie Q11
32 | PMBOK | Prototyping is: | A relatively high-cost strategy for eliciting requirements under an iterative PM approach | A quick way to reduce risk in an Agile PM approach | A useful way to expidite complex deliverables | The origial basis of incremental PM philosophies | A relatively low-cost strategy to take advantage of prior knowledge and experience | Week 4 20 and APG 3.1.2
33 | PMBOK | Which of the following is less likely to take place during the proejct execution phase? | PM classifies stakeholders | PM negotiates and manages change | PM builds relationships | Most resources are expended | Realisation of the organisations strategy and ambition | Bernie slides wk 7 sl5
33