## Last Month
MONTH 8
MONTH | Aurhorised current budget (BAC) | Earned Value (EV) for Month | EV Cumumative | Actual Cost (AC) for month | Cummulative AC | Planned Value (PV) (assessed) for month | PV (assessed) Cumulative | SV | CV | CPI at end of month | SPI at end of Month | Estimated Cost to Complete (ETC) | Forecast costs at Completion (EAC) | Forecast Cost Variance at Complrtion
1 | 45000000 | 3000000 | 3000000 | 2900000 | 2900000 | 3000000 | 3000000 | 0 | 100000 | 1.0345 | 1 | 40600000 | 43500000 | 1500000
2 | 45000000 | 4000000 | 7000000 | 4100000 | 7000000 | 3500000 | 6500000 | 500000 | 0 | 1 | 1.0769 | 38000000 | 45000000 | 0
3 | 45000000 | 4000000 | 11000000 | 3800000 | 10800000 | 3800000 | 10300000 | 700000 | 200000 | 1.0185 | 1.068 | 33381818.1818 | 44181818.1818 | 818181.8182
4 | 45000000 | 7000000 | 18000000 | 6700000 | 17500000 | 7000000 | 17300000 | 700000 | 500000 | 1.0286 | 1.0405 | 26250000 | 43750000 | 1250000
5 | 45000000 | 6000000 | 24000000 | 5900000 | 23400000 | 5500000 | 22800000 | 1200000 | 600000 | 1.0256 | 1.0526 | 20475000 | 43875000 | 1125000
6 | 45000000 | 6000000 | 30000000 | 5900000 | 29300000 | 6500000 | 29300000 | 700000 | 700000 | 1.0239 | 1.0239 | 14650000 | 43950000 | 1050000
7 | 45000000 | 5500000 | 35500000 | 4700000 | 34000000 | 4500000 | 33800000 | 1700000 | 1500000 | 1.0441 | 1.0503 | 9098591.5493 | 43098591.5493 | 1901408.4507
8 | 45000000 | 4700000 | 40200000 | 4600000 | 38600000 | 4500000 | 38300000 | 1900000 | 1600000 | 1.0415 | 1.0496 | 4608955.2239 | 43208955.2239 | 1791044.7761
9
10
11